## Slide 1: Enigma VX V22 Kick Off Meeting
Ofer Sutton
Jan 2026

## Slide 2
Agenda
01 | Background & Scope
02 | Features & Functionalities
03 | Service Providers & Deployment plan
04 | Timelines
05 | Labs
06 | Training
07 | Main Risks
08 | Next steps

## Slide 3: Background
Country - “ Brine”
Customer - NIA (National Intelligence Agency )
    Existing customer, very veteran with our products
    First deployment in 2012 was VBW 5 + Reliant 11
    Second deployment in 2018 was Vantage V19 & Reliant 12
    2 x GI2-M
  Prime (Cyborg)
    Very high standards
    Highly technical and demanding
    Very proficient in our products

## Slide 4: Relationship Flow
NIA
(End User)
Cyborg
S3Tel
Syborg (Cognyte)
Telecom Service Providers
TRA
3rd Party HW CFE

## Slide 5: Enigma Core Team
Regional Business Unit
Yossi Rabanian
Jonathan Levkowitz
Stanislav Velev
Site Team
Vikas Sethi
Vijay Jayakumar
Vijesh George
Technical services
Avner Malka - Network
Yaniv Ram - SE
Sharon Aviram - NPI
Ramesh Ravi. - SI
R&D
Nesi Haver – PDM
Simona Simion – QA
Product
Chemi Katz - PSM
Architecture
Lev Finkel
Avi Louie
Customer success
Amir Pinto
Program GCO
Ofer Sutton
Prime Cyborg
Ravi Kumar Blaize Samuael
Gadhwal Hari Vivek Singh
Satish Byregowda Mohit Naik

## Slide 6: Enigma V 22 – Project Details
Project name – “Enigma - VX new business Model”
Project code – TBD
PO Date Jan 7th, 2026
Unique and strategic deal for Cognyte!!
    Subscription model for 5 year for VX (until Dec 2031)
    TI (Gi2s and Hives) in subscription model for 5.5 years (until Dec 2031)
    DI included – Nexyte over VX for STT

## Slide 7: Project High-Level Scope
  New VX V22 BE
  FE modernization
  LBS modernization
  V19 and V22 Side-by-side with FEs dual delivery
  TC Migration (Targets, Users, Content)
  5G support for telephony and LBS
  V19 system stays as an archive system for additional 1 year (starting ARO+15M)
  2 x Gi2s with 5G support and 2 x Hives with 5G support
  STC FE expansion

## Slide 8: Program Assumptions
HW is CFE – locally bought by Prime
    All assembly and staging work will be done by Prime (Cyborg)
Communication and Infrastructure under prime responsibility
    IPD to be shared by Cognyte for Infra guidelines and Installation
Program is composed of 1 deployment phase (V22.14)
HW provided by Cognyte - Packet Brokers & Load balancers
No remote connection to the site
Current links to captive will be used for V22 side-by-side

## Slide 9: V22 Preliminary Training and Scoping Event
  We will conduct an early training and Scoping event, for V22, with end-user
  Motivation:
    Early engagement with V22 and feedbacks from end user at early stage
    Ease out the process of transition from v19 and V22 from end user perspective
    Highlighting the additional value of V22 over V19
  Scheduled Feb 8, 2026, in Romania office
  End user participants:
    Project team (2 - 3 persons)
    Operational team (2 - 3 persons)
  Will be followed by 1- 2 days of scoping and scoping sign-off
  Required: Methodology trainer for the training & Scoping document

## Slide 10: Program Guidelines
All communication to be done through PjM/ Local team
All email via Syborg emails addresses
All documentations to be labeled as Syborg
Special travel arrangements – PjM will update when relevant

## Slide 11: Features & Functionalities

## Slide 12: Features and Functionalities
Feature Excell is part of the contract (Features functionalities_17122025-clean.xlsx)
The Excell contains 293 items raised by End user
Each item was categorized prior to PO based on the table bellow
“Supported” and “Partially supported” categories are already part of V22.14
Supported in V22 | 191
Not supported in V22 (out of scope) | 61
Partially supported in V22 | 8
In the roadmap | 26
Works as designed | 2
Chart: 
| Supported | Not supported | Partially supported | Roadmap | WAD
 | 196 | 61 | 8 | 26 | 2

## Slide 13: Enigma V22 Scope
Package | Scope
Basic Package | Fully sized BE upgrade to handle all CSPs with Side-by-Side approach including a buffer for future expansions Complete Front-End Modernization for all technologies 2G/3G/4G/5G/ISP/PSTN Security enhancements - Data-at-flight communication security between security sensitive components New TCS Target-Centric system LBS (Location Based Services) for 2G, 3G, 4G
Add on Packages | Next Generation Mass Profiling: Router Profile, Mobile-Router Association, VPN Detection and Application Classification Hidden Relation Analytics (4*chat HR applications & 8*VoIP HR applications) STT (Speech to Text) in TCS (Target Centric System) NAT Translation (CGNAT Correlation) VoLTE Roaming for Zain, STC and Batelco
Upon SP readiness | 5G Stand Alone Technology LBS Support for 5G

## Slide 14: Deployment Plan

## Slide 15: Service Providers

## Slide 16: Side By Side Operation
NAS (Content)
NAS (Content)
Sybase(TC)
Sybase (TC)
GPDB(Index)
GPDB (Index)
HDFS(Profiles)
HDFS(Profiles)
Vx.22 BE System
Vx.19.8.10 BE System
Unified Frontends
Data Query
Data Query
AD
AD
Target Migration
Target Provisioning
Dual Data Delivery
TC & DC
Target Provisioning
No sync of user data

## Slide 17: V19 Cut-Off To V22
NAS (Content)
NAS (Content)
Sybase(TC)
Sybase (TC)
GPDB(Index)
GPDB (Index)
HDFS(Profiles)
HDFS(Profiles)
Vx.22 BE System
Vx.19.8.10 BE System
Unified Frontends
Data Query
Data Query
AD
AD
Target Provisioning
Dual Data Delivery
TC & DC
Target Provisioning
Disable target provisioning
Stop data delivery to vx19.8.10 BE
No sync of user data
Target Migration

## Slide 18: Deployment Process
Vx.19.X System
Dual Delivery
of 3 SPs FEs + 1 small
T 2 – SW Installation
T 3 – Side-by-side
SBS Tandem work
Vx19.x & Vx22.x
Vx.22 New Sys Deployment
Vx.22 as the main operational system
T 4 – New Steady State
Vx.19.X as
Archive system 1Y
T 1 - Infra Deployment
3 SP FE Modernization
Small SPs FEs
ARO
ARO + 7M
ARO + 15M
ARO + 12M
Start of Subscription
Cut-Off Date

## Slide 19: Detailed Planning

## Slide 20: Side by Side Upgrade Scheme
Batelco
Zain
ISP
WiFi Offload
Mobile CS
2G/3G/4G PS
Mobile VoLTE
WiFi offload
PSTN
Mobile CS
2G/3G/4G PS
Mobile VoLTE
Fixed VoIP
SIP Trunking
STC
Mobile CS
2G/3G/4G PS
Mobile VoLTE
Fixed VoIP SIP Trunking WiFi offload
Infonnas
Etisalcom
Neutel
Rapid Telecom
BIX
Kalaam
North star
Viacloud
ISPs
Vantage X
Monitoring Center
Decoding
Health Monitoring
Operators
Analysts
Administrators
Decoding
Metadata Processing
Mass IP Collection
Mass Telephony Collection
Target Interception
Investigation Management
Location Analytics
Content Analysis
Metadata Analysis
Decoding
Enrichment
Mass DB
Target DB
Central Storage
Collection
Processing
Storage
Investigation & Analytics Engines
GPDB
Network Collection & Interception
ISP
ISP
Vantage X
Monitoring Center
Decoding
Health Monitoring
Operators
Analysts
Administrators
Decoding
Metadata Processing
Mass IP Collection
Mass Telephony Collection
Target Interception
Investigation Management
Location Analytics
Content Analysis
Metadata Analysis
Decoding
Enrichment
Mass DB
Target DB
Central Storage
Collection
Processing
Storage
Investigation & Analytics Engines
GPDB
Vx.19.X - Existing
Vx.22 - New
Solution Deployment Principles
V22 Deployment :
Unified FE sites (Dual delivery)
Duplicate BE sites (Vx.19.X existing + Vx.22 New)
Fully sized Vx.22 BE system
Vx.19.X – Existing FEs

## Slide 21: Timeline

## Slide 22
2025
2027
Preparations
Deployment
Acceptance & Dual deliery
TI Delivery
Today
2025
0.5 days
Jan 7
100%
Initial BOM
5.5 days
Jan 14 - Jan 21
100%
Site Survey
5.5 days
Feb 4 - Feb 11
Scoping
May 1 - Jun 30
75%
BE new rack Installation & All servers Comission
Jul 1 - Jul 16
2.3 wks
New GPDB installation and integration
1.7 wks
Jul 19 - Jul 30
SW installation & stabilization
108.5 days
May 1 - Sep 30
FE Side by side
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
2026
Dec
Jan
Feb
Aug 1 - Aug 30
LBS verifications (MA)
Aug 1 - Dec 31
4 FE sites (1 small SP, STC, Batelco, Zain, )
2027
30.4 wks
System Acceptance
Strat Of Subscriprsion
Apr 30
30.4 wks
Dual Delivery Period
5 FE Sites (small operators)
Cut Over
Apr 30
8.5 wks
4 wks
21.7 wks
Sep 1 - Mar 31
Sep 1 - Mar 31
Feb 1 - Mar 31
56.5 days
Feb 11 - Apr 30
CFE Procurement & none-FE
Dec
PO
Dec 1
EUC
Dec 15
Start Of Warranty
Jun 21
2 wks
HW Delivery
3 wks
System Installation
1 wk
SAT
Custom Release
May 10
Apr 26 - May 10
May 24 - Jun 14
Jun 14 - Jun 21
Jan 7
PO
Mar
5.5 days
Apr 30 - May 7
Site ready
2.5 days
Feb 15 - Feb 18
V22 EU Demo & Taining
Apr
8.4 wks

## Slide 23
2026
2027
Preparations
Deployment
Acceptance & Dual deliery
Today
2026
0.5 days
Jan 7
100%
Initial BOM
5.5 days
Jan 14 - Jan 21
100%
Site Survey
5.5 days
Feb 4 - Feb 11
Scoping
May 1 - Jun 30
75%
BE new rack Installation & All servers Comission
Jul 1 - Jul 16
2.3 wks
New GPDB installation and integration
1.7 wks
Jul 19 - Jul 30
SW installation & stabilization
108.5 days
May 1 - Sep 30
FE Side by side
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
2027
Jan
Feb
Mar
Aug 1 - Aug 30
LBS verifications (MA)
Aug 1 - Dec 31
4 FE sites (1 small SP, STC, Batelco, Zain, )
30.4 wks
System Acceptance
Strat Of Subscriprsion
Apr 30
30.4 wks
Dual Delivery Period
8.4 wks
5 FE Sites (small operators)
Cut Over
Apr 30
8.5 wks
4 wks
21.7 wks
Sep 1 - Mar 31
Sep 1 - Mar 31
Feb 1 - Mar 31
56.5 days
Feb 11 - Apr 30
CFE Procurement & none-FE
Jan
Jan 7
PO
Apr
5.5 days
Apr 30 - May 7
Site ready
2.5 days
Feb 15 - Feb 18
V22 EU Demo & Taining

## Slide 24: Program Management

## Slide 25: Program Routines
Internal
    Daily FIR
    Weekly Core team
    Monthly Management status
    Monthly Email progress report
External
    Scoping
    Weekly project meeting
    Quarterly Management Meeting
    Ad-Hoc meetings

## Slide 26: Labs

## Slide 27: Labs
In Cognyte
Lab#1 – Service lab with V19 (same version as on site)
Lab#2 – Fresh installation of V22
FE with dual delivery to both labs
  Both labs will need
    Mobile Arts GMLC & simulators for QA
    NG probe and ODIN/GL simulator for QA
    Grafana enterprise license (MND)

## Slide 28: Training

## Slide 29: Training for V22
Early training V22 (scheduled week of Feb 8th in Romania)
3 x V22 hands-on training session for organization #1 (NIA)
3 x V22 hands-on training session for organization #2 (BDF)

## Slide 30: Risks

## Slide 31: Main Risks
Risk # | Risk type | Risk description | Severity | Probability | Risk score | Mitigation
1 | BWC and Delayed V22 Approval | Extended efforts Delayed start of subscription and revenue. Penalties | 4 | 4 | 16 | Fully Mapped BWC document and Tech Spec in place. Early training on V22 Draft SAT as part of contract
2 | CFE and infrastructure readiness | As Above | 3 | 5 | 15 | SOW plan to reflect the dependencies, no start before full infra readiness Close monitoring of partner progress
3 | CFE BOM gaps | BOM gaps may be attributed to Cognyte | 4 | 3 | 12 | BOM review done prior to PO Buffer H/W taken by Cognyte as part of BOM Buffer H/W taken by partner
4 | Side-by-Side operations | End user will be able to compare between the V19 and the new V22 system. | 3 | 3 | 9 | Demonstrate to Cyborg as soon as possible and get approval HO the system to end user only after target migration to V22 is completed
 | Probability |  |  |  | 
Severity | 1 | 2 | 3 | 4 | 5
 | 2 | 4 | 6 | 8 | 10
 | 3 | 6 | 9 | 12 | 15
 | 4 | 8 | 12 | 16 | 20
 | 5 | 10 | 15 | 20 | 25

## Slide 32: Next Steps
# | Activity | Owner | Completion Date | Status | Comments
1 | Internal KOM | Syborg | Jan 15, 2026 | Done | 
2 | Preliminary V22 training (In Romania) | Syborg | Feb 9, 2026Feb 11,2026 | In progress | Emil will lead
3 | Scoping (In Romania) | Syborg | Feb 10, 2026Feb 11, 2026 | In progress | Scoping Document needs to be shared with Prime 28/1/2026
4 | CFE HW procurement | Cyborg | Jan 20,2026May 2, 2026 | Started | 
5 | Gate 0 | Syborg | Feb 15, 2026 |  | 
6 | Strategy | Syborg | Waiting for allocation from PH |  | 

## Slide 33: Thank you, And Good Luck!