## Samba VX22.10V8.0 site plan cha
Month | [9 empty] | Janury | [19 empty] | February | [11 empty] | March |  |  |  | April |  |  |  |  | May |  |  |  | June
Week Start | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2026-01-05 |  |  |  |  | 2026-01-12 |  |  |  |  | 2026-01-19 |  |  |  |  | 2026-01-26 |  |  |  |  | 2026-02-02 |  |  |  |  | 2026-02-09 |  |  |  |  | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14
Week end | 2024-11-29 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2024-12-27 | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2026-01-09 |  |  |  |  | 2026-01-16 |  |  |  |  | 2026-01-23 |  |  |  |  | 2026-01-30 |  |  |  |  | 2026-02-06 |  |  |  |  | 2026-02-13 |  |  |  |  | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26 | 2027-04-02 | 2027-04-09 | 2027-04-16 | 2027-04-23 | 2027-04-30 | 2027-05-07 | 2027-05-14 | 2027-05-21 | 2027-05-28 | 2027-06-04 | 2027-06-11 | 2027-06-18
Week Topic | Week 62 | Week 63 | Week 64 | Week 65 | Week 66 | Week 67 | Week 68 | Week 69 | Week 70 | Week 01 |  |  |  |  | Week 02 |  |  |  |  | Week 03 |  |  |  |  | Week 04 |  |  |  |  | Week 05 |  |  |  |  | Week 06 |  |  |  |  | Week 07 | Week 08 | Week 09 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52 | Week 53 | Week 54 | Week 55 | Week 56 | Week 57 | Week 58 | Week 59 | Week 60 | Week 61 | Week 62 | Week 63 | Week 64 | Week 65 | Week 66 | Week 67 | Week 68 | Week 69 | Week 70 | Week 71 | Week 72 | Week 73 | Week 74 | Week 75 | Week 76
Project Milestones
Site Activity - VX
[11 empty] | Block 6 new Inst. TCS | Block 7 Data migration + Enabling Dual marking |  |  |  |  | Data Integrity Validation, Compare R12 Vs TCS |  |  |  | Stabilization |  |  |  | Pre-SAT |  |  |  |  | SAT |  |  |  |  | SAT |  |  |  |  | bug fixes | bugf Fixes
July
Dev
GA LAB
Project LAB
Resources / Holiday
PDM | [9 empty] | PDM |  |  |  |  | PDM |  |  |  |  | PDM |  |  |  |  | PDM |  |  |  |  | PDM |  |  |  |  | PDM
[10 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
SI | [9 empty] | SI |  |  |  |  | SI |  |  |  |  | SI |  |  |  |  | SI |  |  |  |  | SI |  |  |  |  | SI
[10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
QA-GA
QA-Project | [9 empty] | QA-Project |  |  |  |  | QA-Project |  |  |  |  | QA-Project |  |  |  |  | QA-Project |  |  |  |  | QA-Project |  |  |  |  | QA-Project
[10 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
IP
Telephony
INFRA
DBA
BD
UF | [10 empty] | UF |  |  |  | UF |  |  |  | UF |  |  |  | UF |  |  |  | UF |  |  |  | UF |  |  |  | UF
[10 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
NPI
DF - Servers
MOPS
FS
Telephony
Formulas:
February = [February, row above]+4
March = [March, row above]+4
April = [April, row above]+4
May = [May, row above]+4
June = [June, row above]+4
Janury = [Janury, row above]+4
Note on AV9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: - PPE Servers Platform installation -> GAD ->OCR ->Exposys ->Import ->Auto import ->Decoding Fax - Backed Decoding Platform Installation/Configuration. BOS -> IPPS - CRS Platforms. BOS -> DF
Note on AV21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: - - OCP cluster Installation - Inventory Data migration - Vault data migration - Automation and MnD Platform migration Reply: - K8S Installed Reply: To allocate NPI - to make sure Remote connectivity is working properly
Note on BD21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pre-Requisite: DB machines (Platform Installation) TC_DB upgrade (NPI support) - Sanity - GPDB - DLS -Sanity - to allocate (DBA, NPI)
Note on BG21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: - KMP Installation - BLS-MS &DF-MS &BLS-Infra - APPRESDB/VLAP/OSM/MPS - Platforms DC/TC- upload config Reply: Cut over to K8S Reply: UF DBA (BoS) : GPDB SBS enablement

## Strategy Planing
year | 2025 | 2026 | [11 empty] | 2027
Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Calendar months | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01
TI Delivery | 2025-01-01: PO EUC; 2025-03-01: Non-CFE Procedurement and Hardware delivery; 2025-06-01: System installation On site and SAT
TI training
Drop 1 -New Vx SBS | 2025-02-01: CFE and Non-CFE HW Procurement; 2025-05-01: CGNAT Samples; 2026-04-01: Cutover
| CDR | VX Based Training and Demo | Export License approval |  |  |  | New Vx ATP submission for BE and FE
| Final BOM & SPG |  |  |  | BE HW SW Infra Readiness 3rd Party Software/Infra (OS and VM) |  | GPDB SW Integration and Verification and New VX SW Installation VX 22.12 | New VX SW Integration TRR VX 22.14 | BE Internal Verification and Pre-SAT with Cyborg and SAT VX22 with End-user |  | Add One more New V22 UMD LBS to work with New MA Hardware | V22 and LBS SP Traffic Migration to New MA Software and Hardware | TC migration from V19.x to V22.14 | MND Calibration
| Site survey BE and FE | [8 empty] | CGNAT Integration (12 FE Sites) |  | CGNAT SAT
[8 empty] | LBS integration (MA) with VX 22.14 and TRR with OLD MA Hardware | Small SP# 1 IP Integration , Batelco Active Fixed VIMS ( 1 Site) Integration Side by Side and TRR + SG UMD + New MC on GSA | Batelco Internal QA LBS ,PSTN Active Solution | STC FE MPD & ISP installation and Integration ( 2 FE) + Zain FE MPD & ISP installation and Integration ( 2 FE) | STC Internal QA IP MPD- and ISP - SAT | Small SP Cutover | “Small service Providers” Integration ( 5 Sites) | Small SP 1,2,3 Internal Verification with Cyborg
[8 empty] | Small SP Cutover | Small SP# 1 Internal SAT with Cyborg and End-user |  |  | STC Internal QA LBS and CS SAT |  |  | Small SP 1,2, Internal verification with Cyborg
[5 empty] | FE HW Readiness and SW Infra Readiness( Total 15 FE)- Sp#1,Sp#2,Sp#3 and All Small SP FE Sites |  |  |  |  | Batelco MPD and ISP FE connection (4 sites) | Batelco Internal QA IP MPD- and ISP - SAT ,Batelco LBS and CS SAT | Zain Internal QA IP MPD- SAT
[5 empty] | After 2 weeks of FE HW - CS (FS and VTPS) 3rd Party Software/Infra installation all Sp#1,Sp#2,Sp#3 9 Sites Side by Side |  |  | Sp#1,Sp#2,Sp#3 FE CS Software installation and Integration (9 Sites) |  | CS TRR all SP |  | Zain Internal QA LBS and CS SAT
IPD for FS Cluster and 3rd Party Software amd Infra Readiness for FE

## Tasks
Last updated 16/02/2026
ID | Subject | Sub- type | Owner | Task | SOW Date (end date) | Due Date (end date) | Closed date | Status | Notes
Vantage x V22
1 | Scoping | Documentation | Syborg | Prepare and share the scoping document with Cyborg for review | 2026-02-10 | 2026-01-28 | 2026-02-04 | Closed | Might be 2-3 days delay due absences of product manager
2 |  | Documentation | Cyborg | Review the scooping document and provide feedbacks | 2026-02-17 | 2026-02-03 | 2026-02-07 | Closed | Will be move accordingly
3 |  | Scoping | Cyborg | Scoping will be done in Romania after V22 demo - 11 or 12 Feb | 2026-02-07 | 2026-02-12 | 2026-01-12 | Closed
|  | Scoping | Syborg | Submitt final scoping document after the scoping | 2026-02-14 | 2026-02-19 |  | Open
4 |  | Scoping sign off | Cyborg | After scooping Cyborg needs to get end user signoff for the scoping | 2026-02-14 | 2026-02-26 |  | Open
5
6 | Demo & Training | Demo/training event |  | Agreed to have the meeting in Romania Feb 9,10,11 Feb | 2026-02-28 | 2026-02-11 | 2026-01-12 | Closed
7 |  | Demo/training agenda |  | Prepare and share the agenda of the demo event with Cyborg | N/A | 2026-01-19 | 2026-01-19 | Closed
8
9 | Site readiness | Infra | Syborg | For all 15 FE High Level , Rack Layout and Power Requirement shared with Prime | 2026-01-31 | 2026-01-11 | 2026-01-11 | Closed
10 |  | Site survey | Cyborg | Site survey needs to be schedules with all service providers and completed ASAP | 2026-01-24 | 2026-01-25 |  | Open | • Completed for BE - points raised to agency waiting for the confirmation. • For STC - Done. Waiting for final space confirmation. • Batelco - Planed for 26/01/2026 - 1 site was done site 2 pending space issues. • Zain - Sanad done and confoirmed. Toobli is pending approval to conduct.
11 |  | Questionairs | Syborg | Syborg to shared with Cyboerg the Questioanirs CGNAT | N/A | 2026-02-05 | 2026-02-02 | Closed | • R&D is working on the questionnaires
|  | Questionairs | Cyborg | Reply on the questionairs is pending from service providers |  | 2026-02-28 |  | Open
12 |  | Samples from service providers | Cyborg | CGNAT Samples from STC, Batelco and Zain | 2026-05-27 |  |  | Open | • After finalization of Questionairs (point above) the samples can be collected
13 |  | Site readiness by service provider and agency | Cyborg | Major service provider - Infrastructure readiness in order to accept the HW to the site | 2026-04-30 | 2026-04-30 |  | Open
14 |  | Final Site readiness | Cyborg | Infrastructure, Rack mounted and positioned in SP, OS installed base on IPD shared by Syborg, NetApp installed and running. | 2026-06-27 | 2026-06-30 |  | Open
15 | V22 HW(CFE) | BOM | Syborg | HW and SW BOM approval for procurement - Shared with Cyborg (Mr. Anoop) | 2026-01-31 | 2026-01-31 | 2026-01-26 | closed | SW BOM shared 26/01/2026
16 |  | HW procurement | Cyborg | Start the procurement process with 3rd party vendors | 2026-05-02 | 2026-05-02 |  | Open | Need to confrim with Mr. Anoop that proccess is ongoing
| Remote connection | remote connection description | Syborg | Will prepare a docunent describing the remote connection policy and guidelines | N/A | 2026-02-28 |  | Open
|  | Remote connection approval | Cyborg | Remote connectin guidelines to be discussed with end user and see if they can be apporoved | N/A | 2026-03-28 |  | Open
Tactical systems
1 | TI HW delivery | EUC | Cyborg | Need to get the signed EUC so export license can be applied | 2026-01-14 | 2026-01-14 | 2026-01-26 | closed | In Delay - Export license request has not been submitted yet as we do not have the EUC signed
2 |  | Export license | Syborg | Export license approval | 2026-03-11 | 2026-03-11 |  | Open
3 |  | Shipping documents approval | Cyborg | will be shared 2 weeks before shipment | 2026-04-29 | 2026-04-29 |  | Open
4 |  | HW delivery | Syborg | After receiving Export licenses and shipping documents approved | 2026-05-13 | 2026-05-13 |  | Open
| 3rd country TI training | Location | Syborg | Need to check where it is possible countries to activate and demotrarate system (cyprus is not allowed any more it can be done only on remote system in HQ) | 2026-02-28 | 2026-02-28 |  | Open
|  | Agenda | Syborg | Compile and share agenda for that training | 2026-03-28 | 2026-03-28 |  | Open
5 | Site readiness | Power requirements | Syborg | Syborg to share specification for external batteries | 2026-06-03 | 2026-02-19 |  | Open | Need to update the scoping document with power requirement
Focus for next week

## SOW Timeline
year | 2025 | 2026 | [11 empty] | 2027
Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Calendar months | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01
TI Delivery | 2025-01-01: PO EUC; 2025-03-01: Non-CFE Procedurement and Hardware delivery; 2025-06-01: System installation On site and SAT
TI training
Drop 1 -New Vx SBS | 2025-02-01: CFE and Non-CFE HW Procurement; 2025-05-01: CGNAT Samples; 2026-04-01: Cutover
| CDR | VX Based Training and Demo | Export License approval |  |  |  | New Vx ATP submission for BE and FE
| Final BOM & SPG |  |  |  | BE HW SW Infra Readiness 3rd Party Software/Infra (OS and VM) |  | GPDB SW Integration and Verification and New VX SW Installation VX 22.12 | New VX SW Integration TRR VX 22.14 | BE Internal Verification and Pre-SAT with Cyborg and SAT VX22 with End-user |  | Add One more New V22 UMD LBS to work with New MA Hardware | V22 and LBS SP Traffic Migration to New MA Software and Hardware | TC migration from V19.x to V22.14 | MND Calibration
| Site survey BE and FE | [8 empty] | CGNAT Integration (12 FE Sites) |  | CGNAT SAT
[8 empty] | LBS integration (MA) with VX 22.14 and TRR with OLD MA Hardware | Small SP# 1 IP Integration , Batelco Active Fixed VIMS ( 1 Site) Integration Side by Side and TRR + SG UMD + New MC on GSA | Batelco Internal QA LBS ,PSTN Active Solution | STC FE MPD & ISP installation and Integration ( 2 FE) + Zain FE MPD & ISP installation and Integration ( 2 FE) | STC Internal QA IP MPD- and ISP - SAT | Small SP Cutover | “Small service Providers” Integration ( 5 Sites) | Small SP 1,2,3 Internal Verification with Cyborg
[8 empty] | Small SP Cutover | Small SP# 1 Internal SAT with Cyborg and End-user |  |  | STC Internal QA LBS and CS SAT |  |  | Small SP 1,2, Internal verification with Cyborg
[5 empty] | FE HW Readiness and SW Infra Readiness( Total 15 FE)- Sp#1,Sp#2,Sp#3 and All Small SP FE Sites |  |  |  |  | Batelco MPD and ISP FE connection (4 sites) | Batelco Internal QA IP MPD- and ISP - SAT ,Batelco LBS and CS SAT | Zain Internal QA IP MPD- SAT
[5 empty] | After 2 weeks of FE HW - CS (FS and VTPS) 3rd Party Software/Infra installation all Sp#1,Sp#2,Sp#3 9 Sites Side by Side |  |  | Sp#1,Sp#2,Sp#3 FE CS Software installation and Integration (9 Sites) |  | CS TRR all SP |  | Zain Internal QA LBS and CS SAT
IPD for FS Cluster and 3rd Party Software amd Infra Readiness for FE

## SOW 3.2
MS | Description | Task Duration | MS start date/ Predecessors | Accumulated duration | End _date | Owner | Description
Project timeline
1. | Project Award, |  | ARO |  |  | Prime | After Receipt of Order (ARO) and contract signature.
| Upon issuance of an order to Syborg |  |  |  | 7.01.2026 |  | PO received by Syborg and approved.
Payment MS#1 – Set-Up Fee
2. | End-user Certificate for GI2-S, Hive and VX | 1 wks | MS#1 | 1 wks | 14.01.2026 | Prime, End-user | Separate Certificate required for Tactical and for Vantage X
3. | Export License approval GI2-S, Hive and VX | 8 wks | MS#2 | 9 wks | 11.03.2026 | Syborg | Based on End-user Certificate
4. | Site Survey | 1 wks | MS#1 + 1wks | 2 wks | 21.01.2026 | Prime, Syborg | A verification checklist will be determined prior to this activity.
5. | CGNAT Samples | 20 wks | MS#1 | 20 wks |  | Prime, Customer | CGNAT captures/samples to be shared with Syborg in order to develop the interfaces.
[5 empty] | 27.05.2026 |  | Any delay in this MS will impact on the general project timelines and delay will not be attributed to Syborg
As mentioned in the technical proposal section 5.4.5.
6. | Final BOM and SPG submission | 1 wks | MS#4 | 3 wks | 28.01.2026 | Syborg | BOM & SPG as per Site survey.
BOM & SPG might change scoping – see BOM comments section
7. | Scoping review | 1 wks | MS#6 | 4 wks | 07.02.2026 | Customer, Prime, Syborg | As the project involves integration with several sub systems a scoping Review process is one of the keys to project success. The scoping review will be held in order to review the project’s detailed design and implementation plan, to ensure that all parties are meeting their objectives and to overcome any obstacles that may arise as the project progresses.
8. | Scoping review Approval ( CDR) | 1 wks | MS#7 | 5 wks |  | Customer | Scoping approval is a prerequisite for the following project Milestones
[5 empty] | 14.02.2026 |  | Upon approval of the scoping by customer the project plan will be frozen, and the project will shift to its implementation phase.
Any delay in signing this MS may impact on the next MS and general project timetable
9. | Classroom-based Training and demo | 1 wks | MS#8+1 wks | 7 wks | 28.02.2026 | Syborg and customer | V22 Overview training for the end user.
10. | CFE and Non-CFE- HW procurement & shipment | 12 wks | MS#7 | 16 wks | 02.05.2026 | Customer, Prime | Customer shall procure the project HW as per the BOM submitted by Syborg and ship it to the agreed location (data center / other facility) – as per section 6
Syborg
New Side By-Side HW
11. | BE HW & 3rd Party SW infrastructure installation at Data Center including LBS New Server (CR02) | 7 wks | MS#10 | 23 wks |  | Prime, Customer | Shipment of HW will be done by customer to Data Center
[5 empty] | 20.06.2026 |  | CFE HW & infrastructure installation will be conducted by Prime 3rd party wiring vendor as detailed in section ‎6.1
Installation of HW will be done as per HW arrival & Availability – Cyborg shall start installation, if possible, even if not all HW is available
Installation will be conducted in Back End data center (BE DC) site
Side-by-side installation of BE HW– floor space as per SPG
Installation will be done by Prime 3rd party wiring vendor – access to be granted by customer
Disposal of HW packing material will be done by customer as per data center guidelines
12. | GPDB HW & SW infrastructure installation at Data Center ( CR02) | 7 wks | MS#10 | 23 wks |  | Prime, Customer | Shipment of HW will be done by customer to Data Center
[5 empty] | 20.06.2026 |  | CFE HW & infrastructure installation will be conducted by Prime 3rd party wiring vendor as detailed in section ‎6.1
Installation of HW will be done as per HW arrival & Availability – Cyborg shall start installation, if possible, even if not all HW is available
Installation will be conducted in Back End data center (BE DC) site
Side-by-side installation of GPDB HW (cluster) – floor space as per SPG
Installation will be done by Prime 3rd party wiring vendor – access to be granted by customer
Disposal of HW packing material will be done by customer as per data center guidelines
13. | BE HW Readiness verification | 1 week | MS#11, MS#12 | 24wks |  | Customer, Prime, Syborg | Verification that all HW has been delivered and installed at the BE DC will be conducted by Syborg and the Prime
[5 empty] | 27.06.2026 |  | HW verification procedure will be shared and agreed in advance
In case of HW verification discrepancies discussion will be held to define the impact and next activities
New Side By-Side System –SW deployment
14. | New GPDB SW Integration | 1wks | MS#13 | 25 wks | 04.07.2026 | Syborg | Integration of side-by-side GPDB cluster - SW
15. | New GPDB SW Integration verification | 1 wks | MS#14 | 26wks | 11.07.2026 | Syborg | Upon completion of this MS –
New GPDB cluster
New BE HW will be available
16. | New Vx SW installation | 2 wks | MS#15 | 28wks |  | Syborg | Syborg will install the new Vx SW version on new HW at customer premises.
[5 empty] | 25.07.2026 |  | Site access for Syborg HQ and local team as well as 3rd party vendors is required.
17. | New Vx SW Integration verification | 4 wks | MS#16 | 32wks | 22.08.2026 | Syborg | Upon completion of this MS –
VX SW on new BE HW will be available
18. | BE internal Verification and | 8 wks | MS#17 | 40wks | 17.10.2026 | Prime, Syborg | As part of the proposal an ATP document submitted and to be agreed upon, this document will be used for system acceptance.
Verification with prime
19. | Location based solution (LBS) integration and verification with VX 22 | 4 wks | MS#16 | 32wks | 22.08.2026 | Prime + Syborg | Integration with Existing LBS solution provided by Mobile Arts
FE Integration and verifications
20. | Sp#1,Sp#2,Sp#3 and Small SP - FE HW Readiness ( Total 15 FE | 20 weeks | MS#10 | 36wks |  | Prime, Customer | Shipment of HW will be done by Prime to SP Data Center
CFE HW & infrastructure installation will be conducted by Prime 3rd party wiring vendor as detailed in section ‎6.1
[5 empty] | 19.09.2026 |  | Installation of HW will be done as per HW arrival & Availability – Cyborg shall start installation, if possible, even if not all HW is available
Installation will be conducted in Back End data center (FE DC) site
Side-by-side installation of FE HW– floor space as per SPG
Installation will be done by Prime 3rd party wiring vendor – access to be granted by customer
Disposal of HW packing material will be done by customer as per data center guidelines
21. | Sp#1,Sp#2,Sp#3 FE CS Software installation and Integration (9 Sites) | 8 wks | MS#10 + 12 Weeks | 36 wks |  | Prime, Syborg | Connectivity and double bandwidth of SP sites in order to allow traffic from SP to flow into new BE
[5 empty] | 19.09.2026 |  | SP FE sites that will not be ready for more than 1 month from the planned date due to site readiness, those FE sites will be considered verified for the completion of this MS, however Syborg will complete the remaining work once FE site will be ready.
Down time will be required
22. | Sp#1,Sp#2, Sp#3 FE CS verification internal | 4 wks | MS#17, | 40 wks | 17.10.2026 | Prime, Syborg | FE sites that will not be ready for more than 1 month from the planned date due to site readiness, those FE sites will be considered as verified for the completion of this MS, however Syborg will complete the remaining work once FE site will be ready.
|  |  | MS#21 |  |  |  | Down time may be required
Dual Delivery for CS All SP
23. | SP#1 Small FE IP SW installation Integration and SAT | 4 wks | MS#17 | 36 wks |  | Customer, Prime, Syborg | Cutover to VX22
[5 empty] | 19.09.2026 |  | SP FE sites that will not be ready for during the testing period (prior to final acceptance) will not affect MS#36. Syborg will complete the remaining work once FE site is ready (during subscription period).
As part of the proposal an ATP document submitted and to be agreed upon, this document will be used for system acceptance.
Down time will be required
24. | SP#1 Batelco FE PSTN Installation, Integration, Internal Verification and PSTN SAT (1 Site) | 4 wks | MS#17 | 36wks |  | Prime, Syborg | Connectivity and double bandwidth of SP sites in order to allow traffic from SP to flow into new BE
[5 empty] | 19.09.2026 |  | SP FE sites that will not be ready for during the testing period (prior to final acceptance) will not affect MS#36. Syborg will complete the remaining work once FE site is ready (during subscription period).
Down time will be required
25. | SP#1 Batelco FE MPD & ISP installation and Integration (4 FE) | 4 wks | MS#22 | 40wks |  | Customer, Prime, Syborg | Connectivity and double bandwidth of SP sites in order to allow traffic from SP to flow into new BE
.
[5 empty] | 17.10.2026 |  | SP FE sites that will not be ready for during the testing period (prior to final acceptance) will not affect MS#36. Syborg will complete the remaining work once FE site is ready (during subscription period).
Down time will be required
26. | SP#1 Batelco FE Pre-SAT and SAT LBS, CS and IP | 4 wks | MS#18 | 44wks | 14.11.2026 | Customer, Prime, Syborg | SP FE sites that will not be ready for during the testing period (prior to final acceptance) will not affect MS#36. Syborg will complete the remaining work once FE site is ready (during subscription period).
|  |  | MS#19, |  |  |  | For the complete process of GMLC migration please refer to section 4.3.3 in the technical proposal.
MS#25
27. | BE - VX SW Installation and Integration Verification VX 22.14 CGNAT | 8 wks | MS#5+16 wks | 44 wks | 14.11.2026 | Customer, Prime, Syborg | CGNAT Captures/Samples were provided as part of MS#5
.
SP FE sites that will not be ready for during the testing period (prior to final acceptance) will not affect MS#36. Syborg will complete the remaining work once FE site is ready (during subscription period).
Down time will be required
28. | CGNAT SAT | 4 wks | MS#27 | 48 wks | 12.12.2026 | Customer, Prime, Syborg | As part of the proposal an ATP document submitted and to be agreed upon, this document will be used for system acceptance.
29. | SP#2 STC FE and Zain MPD & ISP installation and Integration (4 FE) | 4 wks | MS#25 | 44wks |  | Customer, Prime, Syborg | Connectivity and double bandwidth of SP sites in order to allow traffic from SP to flow into new BE
.
[5 empty] | 14.11.2026 |  | SP FE sites that will not be ready for during the testing period (prior to final acceptance) will not affect MS#36. Syborg will complete the remaining work once FE site is ready (during subscription period).
Down time will be required
30. | SP#2 STC FE CS, LBS, MPD & ISP verification, Pre-SAT and SAT | 4 wks | MS#29 | 48wks |  | Customer, Prime, Syborg | .
[5 empty] | 12.12.2026 |  | SP FE sites that will not be ready for during the testing period (prior to final acceptance) will not affect MS#36. Syborg will complete the remaining work once FE site is ready (during subscription period).
As part of the proposal an ATP document was submitted and agreed upon, this document will be used for system acceptance.
31. | SP#3 Zain FE CS, LBS, MPD & ISP verification, Pre-SAT and SAT | 4 wks | MS#29 | 48wks |  | Customer, Prime, Syborg | .
[5 empty] | 12.12.2026 |  | SP FE sites that will not be ready for during the testing period (prior to final acceptance) will not affect MS#36. Syborg will complete the remaining work once FE site is ready (during subscription period).
As part of the proposal an ATP document was submitted and agreed upon, this document will be used for system acceptance.
Dual Delivery Completed for All Big SP –CS,PSTN, IP and Small SP Cutover to V22
32. | Full TC Migration (Users/Targets/ | 2wks | MS#31 | 50wks |  | Customer, Prime, Syborg | Before migration All V22 test targets and test products should be deleted from the V22 system.
| Products) from V19.x to V22.14 | [5 empty] | Only TC Data and content will be transferred as part of the migration to the new V22 system, TC to DC products will not be transferred to the new system.
[5 empty] | 26.12.2026 |  | After Migration New Targets should be defined in both VX 19.x and VX 22.0 to get Data in Both Systems until we reach MS# 37 (cutover)
New Targets/users/Products will not be syncing automatically or manually between V19.x / V22.x
After Migration Active LBS Targets can be supported either in V19.x or V22.x
33 | V22 and LBS SP Traffic Migration to New MA Software and Hardware | 2wks | MS#32 | 52wks | 9.01.2027 | Prime, Syborg | Shift SP Traffic from Old MA Hardware to New Software /Ma Hardware in New BE Site
34 | “IP Small service Providers” Integration (5 Sites) | 4 wks | MS#33 | 56 wks |  | Prime, Syborg | Cutover to VX22
[5 empty] | 6.02.2027 |  | SP FE sites that will not be ready for during the testing period (prior to final acceptance) will not affect MS#36. Syborg will complete the remaining work once FE site is ready (during subscription period).
Down time will be required
35 | “IP Small service Providers” Verification with Cyborg ( 5 Sites) | 4 wks | MS#34 | 60 wks | 06.03.2027 | Prime, Syborg | SP FE sites that will not be ready for more than 1 month from the planned date due to site readiness, will not be part of the final acceptance and will not affect MS 36 Syborg will complete the remaining work once FE site will be ready (during subscription period).
36 | System Acceptance and commissioning Start of Subscription | 0 wks | MS#35 | 60 wks | 06.03.2027 |  | Achieved upon completion of MS#35
The system acceptance will be performed with the 3 big operators (Batelco, Zain, STC) and with the small operators which will be ready at that point (see relevant remarks of MS 34 and MS 35).
Start of Subscription- Payment MS#2
37 | Final Cutover to Vx22 | 4 wks | MS#36 | 64 wks |  | Customer, Prime, Syborg | Stop New Traffic going to VX 19.x
[5 empty] | 3.04.2027 |  | 19.x Standalone System will be available for 1 year after the Cutover
AMC should be active for 19.x System during the whole period
38 | End of support for V19 Legacy system | 12 months | MS#37 | 116 wks | 03.04.2028 | Syborg

## TI SOW
MS | Description | Task Duration | MS start date/ Predecessors | Accumulated duration | Actual dates | Owner | Description
Project timeline
1. | Project Award, |  | ARO |  |  | Prime | After Receipt of Order (ARO) and contract signature.
| Upon issuance of an order to Syborg |  |  |  | 2026-01-07 |  | PO received by Syborg and approved.
2. | End-user Certificate for GI2-S, Hive | 1 wks | MS#1 | 1 wks | 2026-01-14 | Prime, End-user
3. | Export License approval GI2-S, Hive | 8 wks | MS#2 | 9 wks | 2026-03-11 | Syborg | Based on End-user Certificate
4. | Shipping document approval | 1 wks | MS#1 + 15 wks | 16 wks | 2026-04-29 | Prime, End-user | Shipping document will be shared by Syborg, and end user will have to confirm shipping Documents are OK and goods can depart the country of origin
5. | HW shipment | 2 wks | MS#4 | 18 wks | 2026-05-13 | Customer, Prime, Syborg | Shipping terms are CPT, end user is responsible for clearing HW from customs and transporting it to the site. Payment MS#1 – First Year Subscription
6. | Release from customs | 2 wks | MS#5 | 20 wks | 2026-05-27 | Customer | Shipping terms are CPT, and the end user is responsible for clearing HW from customs and transporting it to the site.
7. | Site readiness | 1 wks | MS#6 | 21 wks | 2026-06-03 | Customer and Syborg | Site visit will be conducted to show that the cars are ready for system deployment.
8. | System installation and testing | 1 wks | MS#7 | 22 wks | 2026-06-10 | Customer, Prime | Customer shall procure the project HW as per the BOM submitted by Syborg and ship it to the agreed location (data center / other facility) – as per section 6
Syborg
9. | SAT / Commissioning | 1 wks | MS#8 | 23 wks | 2026-06-17 | Customer and Syborg | After commissioning subscription will commence.
10. | Training | 1 wks | MS#9 | 24 wks | 2026-06-24 | Syborg