## Slide 1: Enigma 22.14 Project Strategy
Nesi Haver 03/2026
Opening Session

## Slide 2
01 | Welcome - Strategy Session
02 | PO Information
03 | High-level plan (Scope & timeline)
04 | Assumptions
05 | Full kit
06 | Project Risks
07 | Main Milestones (NI)
08 | 
09 | 
Agenda
2

## Slide 3: Strategy Sessions
Monday (March) | Tuesday (March) | May | May | May
Opening Session | Project HLP | Target version | Risk Management | Strategy Closure
Project content 22.14 (shift-left) | Project timeline | SI Plan | Project site Plan | Risk management
 |  | QA plan | MMI Review Outcome | 
Notes: During upcoming we will have almost 11 sessions. Each session is one hour, fewer 1 hour 30, then we will cover all technical aspects in terms of scope, risk management, assumptions, and other coordination that require a I already published the author and the owner that will present his main expertise and domain related to this project.

## Slide 4: Enigma – Customer backgroup
Country: "Brine"
Customer: NIA (National Intelligence Agency)
    Existing customer, very veteran with our products
Deployment History:
  1st deployment : 2012: VBW 5 + Reliant 11
  2nd Deployment 2018: Vantage V19 & Reliant 12
Prime (Cyborg)
  Profile: Very high standards, highly technical
  deeply proficient with our products

## Slide 5: Relationship Flow
NIA
(End User)
Cyborg
S3Tel
Syborg (Cognyte)
Telecom Service Providers
TRA
3rd Party HW CFE

## Slide 6: PO Information
Project name: "Enigma - VX New Business Model"
Code: OTL XXX | Date: Jan 7th, 2026
Strategic Subscription Deal:
  VX – subscription model  5 years (until Dec 2031)
  TI (GI2s, Hives): 5.5 years
  DI: Nexyte over VX for STT

## Slide 7: Project High-Level Scope
Core Deliverables
VX 22.14 BE with FE modernization
LBS modernization (location-based solution)
V19 & V22 side-by-side with dual FE delivery
TC Migration (Targets, Users, Content)
5G support for telephony and LBS
STC FE expansion
V19 system stays as an archive system for additional 1 year (starting ARO+15M)
  2 x Gi2s with 5G support and 2 x Hives with 5G support
Infrastructure:
• 2 x GI2s + 2 x Hives (5G support)
• STC FE expansion
Timeline: V19 stays as archive (ARO+15M through ARO+27M)

## Slide 8: Program Assumptions
# | Program Assumption | Responsibility | Notes
1 | Hardware is CFE and will be locally purchased by Prime | Prime (Cyborg) | Procurement managed locally
2 | All assembly and staging activities will be performed by Prime | Prime (Cyborg) | Includes preparation before deployment
3 | Communication and infrastructure are under Prime responsibility | Prime | Covers networking and site connectivity
4 | IPD will be provided by Cognyte for infrastructure guidelines and installation | Cognyte | Defines installation standards
5 | Program consists of a single deployment phase (V22.14) | Program Scope | No phased rollout planned
6 | Packet Brokers and Load Balancers hardware supplied by Cognyte | Cognyte | Dedicated infrastructure components
7 | No remote connectivity to the site | Site Constraint | All work performed on-site
8 | Existing links to Captive will be used for V22 side-by-side deployment | Infrastructure | Enables parallel environment

## Slide 9: Program Guidelines
All communication to be done through PjM/ Local team
All email via Syborg emails addresses
All documentations to be labeled as Syborg
Special travel arrangements – PjM will update when relevant

## Slide 10: Features & Functionalities
22.14
VDM and PSM

## Slide 11: VX 22.14 – mains
strategic modernization step aligned with product roadmap and customer needs.
Chart: 
Platform Modernization
Migration toward Kubernetes based architecture
Replacement of legacy infrastructure components
Improved scalability and deployment flexibilit
Security and identity improvements
AAA Enrichment and Authentication Enhancement
Platform security hardening.
Improved access control and auditing.
DevOps and Delivery Efficiency
CICD Pipeline Improvement
Faster development & Release cycles
Improved build and deployment automation
Chart: 

## Slide 12: VX 22.14 – mains (Cont’d)
Chart: 
Chart: 
Data & Platform Infrastructure
Databases modernization and replacement.
Platform performance and stability improvements
Infrastructure readiness for future capabilities
User Experience
Introduction of web viewers
Gradual move towards web-based client architecture.
Improve accessibility for investigators.
Upgrade and scratch Installation
Architecture changes
New Cook-book of installation

## Slide 13: VX 22.14 – Timeline
Chart: 
Chart: 
Release Timeline – Major Milestones
Upcoming Version Scope to Capacity Challenge Review
Execution
Start
Planning
Execution
End / GA VRR
Released Version Scope Communication
&
Version Release Kit
Version 22.14 Development
Upcoming Version Scope Introduction
Q3
Q4
Q2
Q1
Scope to Capacity – mid-Dec 2025
Scope Introduction Jan-2026
Execution start Feb-2026
VRR July-2026
2026

## Slide 14: Features and Functionalities
Feature Excell is part of the contract (Features functionalities_17122025-clean.xlsx)
The Excell contains 293 items raised by End user
Each item was categorized prior to PO based on the table bellow
“Supported” and “Partially supported” categories are already part of V22.14
Supported in V22 | 191
Not supported in V22 (out of scope) | 61
Partially supported in V22 | 8
In the roadmap | 26
Works as designed | 2
Chart: 
| Supported | Not supported | Partially supported | Roadmap | WAD
 | 196 | 61 | 8 | 26 | 2

## Slide 15: Service Providers
Notes: Here is the map of the service providers with the existing frontends. In Total (needs to counts) Because this will impact the upgrade duration and the old process, we will work on site.

## Slide 16: Side By Side Operation
NAS (Content)
NAS (Content)
Sybase(TC)
Sybase (TC)
GPDB(Index)
GPDB (Index)
HDFS(Profiles)
HDFS(Profiles)
Vx.22 BE System
Vx.19.8.10 BE System
Unified Frontends
Data Query
Data Query
AD
AD
Target Migration
Target Provisioning
Dual Data Delivery
TC & DC
Target Provisioning
No sync of user data

## Slide 17: V19 Cut-Off To V22
NAS (Content)
NAS (Content)
Sybase(TC)
Sybase (TC)
GPDB(Index)
GPDB (Index)
HDFS(Profiles)
HDFS(Profiles)
Vx.22 BE System
Vx.19.8.10 BE System
Unified Frontends
Data Query
Data Query
AD
AD
Target Provisioning
Dual Data Delivery
TC & DC
Target Provisioning
Disable target provisioning
Stop data delivery to vx19.8.10 BE
No sync of user data
Target Migration

## Slide 18: Deployment Process
Vx.19.X System
Dual Delivery
of 3 SPs FEs + 1 small
T 2 – SW Installation
T 3 – Side-by-side
SBS Tandem work
Vx19.x & Vx22.x
Vx.22 New Sys Deployment
Vx.22 as the main operational system
T 4 – New Steady State
Vx.19.X as
Archive system 1Y
T 1 - Infra Deployment
3 SP FE Modernization
Small SPs FEs
ARO
ARO + 7M
ARO + 15M
ARO + 12M
Start of Subscription
Cut-Off Date

## Slide 19: Detailed Planning

## Slide 20: Side by Side Upgrade Scheme
Batelco
Zain
ISP
WiFi Offload
Mobile CS
2G/3G/4G PS
Mobile VoLTE
WiFi offload
PSTN
Mobile CS
2G/3G/4G PS
Mobile VoLTE
Fixed VoIP
SIP Trunking
STC
Mobile CS
2G/3G/4G PS
Mobile VoLTE
Fixed VoIP SIP Trunking WiFi offload
Infonnas
Etisalcom
Neutel
Rapid Telecom
BIX
Kalaam
North star
Viacloud
ISPs
Vantage X
Monitoring Center
Decoding
Health Monitoring
Operators
Analysts
Administrators
Decoding
Metadata Processing
Mass IP Collection
Mass Telephony Collection
Target Interception
Investigation Management
Location Analytics
Content Analysis
Metadata Analysis
Decoding
Enrichment
Mass DB
Target DB
Central Storage
Collection
Processing
Storage
Investigation & Analytics Engines
GPDB
Network Collection & Interception
ISP
ISP
Vantage X
Monitoring Center
Decoding
Health Monitoring
Operators
Analysts
Administrators
Decoding
Metadata Processing
Mass IP Collection
Mass Telephony Collection
Target Interception
Investigation Management
Location Analytics
Content Analysis
Metadata Analysis
Decoding
Enrichment
Mass DB
Target DB
Central Storage
Collection
Processing
Storage
Investigation & Analytics Engines
GPDB
Vx.19.X - Existing
Vx.22 - New
Solution Deployment Principles
V22 Deployment :
Unified FE sites (Dual delivery)
Duplicate BE sites (Vx.19.X existing + Vx.22 New)
Fully sized Vx.22 BE system
Vx.19.X – Existing FEs

## Slide 21: Timeline

## Slide 22
2025
2027
Preparations
Deployment
Acceptance & Dual deliery
TI Delivery
Today
2025
0.5 days
Jan 7
100%
Initial BOM
5.5 days
Jan 14 - Jan 21
100%
Site Survey
5.5 days
Feb 4 - Feb 11
Scoping
May 1 - Jun 30
75%
BE new rack Installation & All servers Comission
Jul 1 - Jul 16
2.3 wks
New GPDB installation and integration
1.7 wks
Jul 19 - Jul 30
SW installation & stabilization
108.5 days
May 1 - Sep 30
FE Side by side
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
2026
Dec
Jan
Feb
Aug 1 - Aug 30
LBS verifications (MA)
Aug 1 - Dec 31
4 FE sites (1 small SP, STC, Batelco, Zain, )
2027
30.4 wks
System Acceptance
Strat Of Subscriprsion
Apr 30
30.4 wks
Dual Delivery Period
5 FE Sites (small operators)
Cut Over
Apr 30
8.5 wks
4 wks
21.7 wks
Sep 1 - Mar 31
Sep 1 - Mar 31
Feb 1 - Mar 31
56.5 days
Feb 11 - Apr 30
CFE Procurement & none-FE
Dec
PO
Dec 1
EUC
Dec 15
Start Of Warranty
Jun 21
2 wks
HW Delivery
3 wks
System Installation
1 wk
SAT
Custom Release
May 10
Apr 26 - May 10
May 24 - Jun 14
Jun 14 - Jun 21
Jan 7
PO
Mar
5.5 days
Apr 30 - May 7
Site ready
2.5 days
Feb 15 - Feb 18
V22 EU Demo & Taining
Apr
8.4 wks

## Slide 23
2026
2027
Preparations
Deployment
Acceptance & Dual deliery
Today
2026
0.5 days
Jan 7
100%
Initial BOM
5.5 days
Jan 14 - Jan 21
100%
Site Survey
5.5 days
Feb 4 - Feb 11
Scoping
May 1 - Jun 30
75%
BE new rack Installation & All servers Comission
Jul 1 - Jul 16
2.3 wks
New GPDB installation and integration
1.7 wks
Jul 19 - Jul 30
SW installation & stabilization
108.5 days
May 1 - Sep 30
FE Side by side
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
2027
Jan
Feb
Mar
Aug 1 - Aug 30
LBS verifications (MA)
Aug 1 - Dec 31
4 FE sites (1 small SP, STC, Batelco, Zain, )
30.4 wks
System Acceptance
Strat Of Subscriprsion
Apr 30
30.4 wks
Dual Delivery Period
8.4 wks
5 FE Sites (small operators)
Cut Over
Apr 30
8.5 wks
4 wks
21.7 wks
Sep 1 - Mar 31
Sep 1 - Mar 31
Feb 1 - Mar 31
56.5 days
Feb 11 - Apr 30
CFE Procurement & none-FE
Jan
Jan 7
PO
Apr
5.5 days
Apr 30 - May 7
Site ready
2.5 days
Feb 15 - Feb 18
V22 EU Demo & Taining

## Slide 24: Program Management

## Slide 25: Program Routines
Internal
    Daily FIR
    Weekly Core team
    Monthly Management status
    Monthly Email progress report
External
    Scoping
    Weekly project meeting
    Quarterly Management Meeting
    Ad-Hoc meetings

## Slide 26: Labs

## Slide 27: Labs
In Cognyte
Lab#1 – Service lab with V19 (same version as on site)
Lab#2 – Fresh installation of V22
FE with dual delivery to both labs
  Both labs will need
    Mobile Arts GMLC & simulators for QA
    NG probe and ODIN/GL simulator for QA
    Grafana enterprise license (MND)

## Slide 28: Training

## Slide 29: Training for V22
Early training V22 (scheduled week of Feb 8th in Romania)
3 x V22 hands-on training session for organization #1 (NIA)
3 x V22 hands-on training session for organization #2 (BDF)

## Slide 30: Risks

## Slide 31: Main Risks
Risk # | Risk type | Risk description | Severity | Probability | Risk score | Mitigation
1 | BWC and Delayed V22 Approval | Extended efforts Delayed start of subscription and revenue. Penalties | 4 | 4 | 16 | Fully Mapped BWC document and Tech Spec in place. Early training on V22 Draft SAT as part of contract
2 | CFE and infrastructure readiness | As Above | 3 | 5 | 15 | SOW plan to reflect the dependencies, no start before full infra readiness Close monitoring of partner progress
3 | CFE BOM gaps | BOM gaps may be attributed to Cognyte | 4 | 3 | 12 | BOM review done prior to PO Buffer H/W taken by Cognyte as part of BOM Buffer H/W taken by partner
4 | Side-by-Side operations | End user will be able to compare between the V19 and the new V22 system. | 3 | 3 | 9 | Demonstrate to Cyborg as soon as possible and get approval HO the system to end user only after target migration to V22 is completed
 | Probability |  |  |  | 
Severity | 1 | 2 | 3 | 4 | 5
 | 2 | 4 | 6 | 8 | 10
 | 3 | 6 | 9 | 12 | 15
 | 4 | 8 | 12 | 16 | 20
 | 5 | 10 | 15 | 20 | 25

## Slide 32
32

## Slide 33: HLP/Contractual Milestones
Project Type: ARR project/Scratch installation/Upgrade
Phases
  Ph1 – Based version: xxx
    HW readiness
  Ph2 – Based Version: xxx
Contractual Milestones
  HW delivery

## Slide 34: Preliminary Risks
# | Risk | Severity | Mitigation | Owner | Comments

## Slide 35: Full Kit
# |  |  |  |  | 

## Slide 39
Text
1.5B
Text
1.5B
Text
1.5B
Text
1.5B

## Slide 40
Text
1.5B
Text
1.5B
Text
1.5B
Text
1.5B
Text
1.5B
Text
1.5B

## Slide 41
Title here
Text over here Text over here Text over here
Text over here Text over
Title here
Text over here Text over here Text over here
Text over here Text over
Title here
Text over here Text over here Text over here
Text over here Text over
Title here
Text over here Text over here Text over here
Text over here Text over

## Slide 42
Title over here
Text over here text over here text over here over
Title over here
Text over here text over here text over here over
Title over here
Text over here text over here text over here over
Title over here
Text over here text over here text over here over
Title over here
Text over here text over here text over here over

## Slide 43: Thank you!
43

## Slide 44
Chart: 
| Category 1 | Category 2 | Category 3 | Category 4
Series 1 | 4.3 | 2.5 | 3.5 | 4.5
Series 2 | 2.4 | 4.4 | 1.8 | 2.8
Series 3 | 2 | 2 | 3 | 5