## Timeline
Weekly | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-02-01 | 2026-02-08 | 2026-02-15 | 2026-02-22 | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28
calender Weeks END | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02 | 2026-05-09 | 2026-05-16 | 2026-05-23 | 2026-05-30 | 2026-06-06 | 2026-06-13 | 2026-06-20 | 2026-06-27 | 2026-07-04
Weeks | Week 2 | Week3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23
Prep | PO |  |  | KOM | Procurmet shipment and custom clearance
BE | [18 empty] | BE V19.x UDC Creation
Site 1 FE | [17 empty] | Rack Installation Power up and HW Installation |  | FE IP Configuration Prepartion for New TBOS, MDE and SAU | FE IP TBOS Integration and internal verification | FE IP MDE Addition, Integration and internal verification | FE IP SAU Addition and New UDC Integration and internal verification | FE IP Verification with Prime |  | Acceptance Test Procedure - ATP
Site 2 FE | [17 empty] | Rack Installation Power up and HW Installation |  | FE IP Configuration Prepartion for New TBOS, MDE and SAU | FE IP TBOS Integration and internal verification | FE IP MDE Addition, Integration and internal verification | FE IP SAU Addition and New UDC Integration and internal verification | FE IP Verification with Prime |  | Acceptance Test Procedure - ATP