SYSTEM MIGRATION & HARDWARE RESHUFFLING PROJECT

Multi-Backend Delivery Strategy: Vx 19.X → Vx 22.14 on Kubernetes

Project Structure & Execution Plan

| Project Scope | Two interdependent work blocks requiring phased execution |
| --- | --- |
| - Block 1: Hardware - Block 2: Connectivity | Installation & site rebuild BE 22.14 multi-backend delivery |

## 🔗 Critical Dependencies

| Block 1 Must Complete Before Block 2 Begins | Dual-delivery capability depends on hardware stability |
| --- | --- |

# BLOCK 1: HARDWARE INSTALLATION & RESHUFFLING

Phased deployment across two site categories with parallel execution capability

## Site Deployment Strategy Comparison

| Dimension | SMALL SITES | LARGE SITES |
| --- | --- | --- |
| Strategy | Complete Replacement | Phased Upgrade + Repurposing |
| TBOS Action | Replace FFU → TBOS (new) | Replace TBOS → G.16 (new) |
| Legacy TBOS | No legacy TBOS | Repurpose for MDE + SAU |
| Hardware Suite | TBOS, SAU, MDE, UDC (all new) | Mixed: G.16 + repurposed |
| Parallel Operation | Old site unchanged on legacy system | Dual-backend delivery (19.X + 22.14) |
| Complexity | Low (greenfield) | High (migration + repurpose) |

## SMALL SITES: Complete Hardware Replacement

### Overview

Build completely new sites from scratch. Existing legacy infrastructure remains untouched and operational.

### Work Scope

| # | Component | Action |
| --- | --- | --- |
| 1 | TBOS Unit | Replace FFU → Install new TBOS (from procurement) |
| 2 | SAU | Deploy new SAU unit |
| 3 | MDE | Deploy new MDE unit |
| 4 | UDC | Deploy new UDC (dedicated to BE 22.14) |
| 5 | System Integration | All new hardware connects ONLY to new backend system |
| 6 | Legacy Site | NO CHANGES — existing site continues normal operation on old system |

### Key Characteristics

- ✓ Greenfield deployment — no migration complexity

- ✓ Risk isolation — legacy system unaffected

- ✓ Can execute in parallel with large sites

- ✓ Faster execution path

### DECISION REQUIRED

| Owner | Finkel, Lev |
| --- | --- |
| Required Confirmation | Confirm complete new hardware suite (TBOS, SAU, MDE, UDC) for all small sites |
| Timeline Impact | HIGH — Hardware procurement lead time drives critical path |

## LARGE SITES: Phased Upgrade with Equipment Repurposing

### Overview

Replace TBOS units with G.16 models. Decommissioned TBOS units are reused for MDE and SAU. Sites operate in dual-backend delivery mode during transition.

### Upgrade Sequence

| Phase | Action | Details |
| --- | --- | --- |
| 1️⃣ | Procurement | Acquire new G.16 TBOS units |
| 2️⃣ | Reshuffling Plan | Document equipment reallocation (TBOS→MDE, TBOS→SAU mapping) |
| 3️⃣ | TBOS Replacement | Swap existing TBOS with new G.16 units |
| 4️⃣ | Repurpose Legacy | Commission decommissioned TBOS for MDE + SAU roles |
| 5️⃣ | Dual-Delivery Enable | Configure simultaneous delivery to Vx 19.X + Vx 22.14 |

### Multi-Backend Delivery Requirement

During transition, large sites MUST support simultaneous delivery to both backends:

| Backend Version | Status | Notes |
| --- | --- | --- |
| Vx 19.X | Legacy (operational) | Must continue serving production traffic |
| Vx 22.14 | New (being activated) | Parallel testing and gradual traffic migration |

### Key Challenges & Risks

- ⚠ Equipment repurposing complexity — must validate legacy TBOS fitness for MDE/SAU roles

- ⚠ Dual-delivery testing must be exhaustive — network, routing, failover scenarios

- ⚠ Extended site downtime may not be feasible — requires careful scheduling

- ⚠ Configuration complexity increases maintenance burden

### DECISIONS REQUIRED

| Decision Point | Owner | Status |
| --- | --- | --- |
| Confirm G.16 quantity | Haver, Nesi | TBD [PENDING] |
| Approve reshuffling plan | Haver, Nesi + Finkel, Lev | TBD [PENDING] |
| Validate legacy TBOS fitness | Technical Team | TBD [PENDING] |

## Hardware Inventory — BY SITE

Complete this table for each Enigma site. Reference format: G.13, G.14, G.15, G.16, etc.

| Site Name | # TBOS | Type | # SAU | Type | # MDE | Type |
| --- | --- | --- | --- | --- | --- | --- |
| Enigma-01 |  |  |  |  |  |  |
| Enigma-02 |  |  |  |  |  |  |
| Enigma-03 |  |  |  |  |  |  |
| Enigma-04 |  |  |  |  |  |  |
| [Add more rows] |  |  |  |  |  |  |

Owner: Haver, Nesi  |  Status: AWAITING DATA

## Project Metrics — BLOCK 1

| Metric | Target Value | Status |
| --- | --- | --- |
| Total new G.16 TBOS units | [TO BE FILLED] | Pending [PENDING] |
| Small sites to upgrade | [# Sites] | TBD |
| Large sites to upgrade | [# Sites] | TBD |
| Legacy TBOS units available for reuse | [# Units] | TBD |

# BLOCK 2: CONNECTIVITY TO NEW BACKEND 22.14

Kubernetes-based infrastructure with multi-backend delivery capability

🔗 Dependency: Block 1 hardware must be stable before connectivity phase begins.

## Architecture Overview

| Legacy System (Vx 19.X) | New System (Vx 22.14 / K8s) |
| --- | --- |
| - Traditional infrastructure - CRS active - MSMQ for SAU→UDC | - Kubernetes-native - CRS deprecated → MFM - MSMQ or Kafka (TBD) |

## SAU: Multi-Domain Delivery

### Requirement

SAU must simultaneously deliver messages to UDC endpoints in both legacy and new systems.

### Delivery Path Design

| Source | Target UDC | Protocol | Transition |
| --- | --- | --- | --- |
| SAU | Old UDC (Vx 19.X) | MSMQ | No change |
| SAU | New UDC (Vx 22.14) | MSMQ or Kafka? [TBD] | Decision needed |

### 🔴 CRITICAL DECISION

| Owner | Keren, Zhaneta |
| --- | --- |
| Question | Will SAU→New UDC use MSMQ initially with post-cutover Kafka migration, OR implement Kafka from day 1? |
| Options | - Start MSMQ → Phase 2: Kafka - Start Kafka directly (scalability focus) |
| Timeline Impact | HIGH — Affects BE 22.14 readiness & load testing scenarios |

## MDE & Related Components: Dual-Delivery Mode

### Requirement

The following components must be configured to support concurrent delivery to both Vx 19.X and Vx 22.14 backends:

| # | Component | Function |
| --- | --- | --- |
| 1 | MDE | Message Distribution Engine — routes traffic to both backends |
| 2 | EDR | Error Detection & Recovery — monitors delivery to both targets |
| 3 | AA | Automated Audit — logs transactions across dual paths |
| 4 | VR | Validation & Reconciliation — ensures consistency between backends |

### 🔴 OUTSTANDING QUESTION

| Owner | Issler, Shlomo |
| --- | --- |
| Question | Are there additional MDE plugins beyond EDR, AA, VR that must support dual-delivery mode? |
| Impact | Incomplete plugin list → configuration gaps → delivery failures |
| Action | Provide complete list of all MDE plugins that must operate in dual-delivery |

## Infrastructure: PBU, Redis & Support Services

### Components to Deploy

| Component | Purpose | Services | Status |
| --- | --- | --- | --- |
| PBU | Policy-Based Unit | TC GTP, RADIUS, Enrichment | New [PENDING] |
| Redis | In-Memory Store | Caching, Session Mgmt | New [PENDING] |

### ⚠️ DEPENDENCY: PBU & Dual-Delivery Alignment

Question: Does PBU support the dual-delivery patterns required by MDE, SAU, and other components?

| Issue | Severity | Resolution |
| --- | --- | --- |
| PBU may not support dual-backend delivery | HIGH | Schedule joint architecture review meeting (PBU team + delivery design team) |

## Component Migration: CRS → MFM

### Legacy System (Vx 19.X)

| Status | CRS continues operating unchanged |
| --- | --- |
| Service | Configuration Registry Service — maintains existing operation |

### New System (Vx 22.14 on Kubernetes)

| Change | CRS is DEPRECATED |
| --- | --- |
| Replacement | MFM (Message Flow Manager) handles all configuration functions |
| Migration | All CRS functionalities map to MFM equivalents — validate during design phase |

## Block 2 Planning & Execution

### Next Steps

- Schedule Block 2 Architecture Design Meeting

  - Participants: Keren (SAU), Issler (MDE), PBU team, Kubernetes ops

  - Duration: 2 hours

  - Agenda: Finalize MSMQ vs. Kafka decision, list all dual-delivery plugins, resolve PBU constraints

- Create detailed Block 2 implementation roadmap (post-architecture meeting)

- Establish Kubernetes cluster & PBU/Redis deployment

- Initiate CRS→MFM migration planning

# PROJECT SUMMARY & DECISION TRACKING

## Stakeholder Action Items

| Block | Action | Owner | Status |
| --- | --- | --- | --- |
| 1 | Confirm small site hardware specs | Finkel, Lev | Pending [PENDING] |
| 1 | Provide G.16 quantity + hardware inventory | Haver, Nesi | Pending [PENDING] |
| 1 | Approve reshuffling plan | Haver, Nesi | Pending [PENDING] |
| 2 | Finalize SAU→UDC protocol (MSMQ/Kafka) | Keren, Zhaneta | Blocked [DECISION_REQUIRED] |
| 2 | List all MDE dual-delivery plugins | Issler, Shlomo | Blocked [DECISION_REQUIRED] |
| 2 | Schedule PBU dependency review | All stakeholders | Blocked [DECISION_REQUIRED] |

## Critical Path Dependencies

| Phase | Prerequisite | Blocker? | Mitigation |
| --- | --- | --- | --- |
| Block 1 Execute | Hardware procurement | YES | Order immediately upon approval |
| Block 2 Start | Block 1 stability (all sites operational) | YES | Run 72-hr burn-in before proceeding |
| Block 2 Architecture | MSMQ/Kafka decision | YES | Schedule decision meeting within 1 week |

## Success Criteria

### Block 1 Complete

- ✓ All small sites deployed and validated on new system

- ✓ All large sites upgraded with G.16 TBOS units

- ✓ Legacy equipment repurposed for MDE/SAU roles

- ✓ Dual-delivery capability tested (19.X + 22.14 concurrent)

- ✓ 72-hour burn-in passes with zero errors

### Block 2 Complete

- ✓ Kubernetes infrastructure operational

- ✓ PBU + Redis deployed and validated

- ✓ SAU multi-domain delivery (MSMQ/Kafka) functional

- ✓ MDE dual-delivery mode tested across all plugins

- ✓ CRS→MFM migration complete, no functionality gaps

- ✓ Load testing passes: sustained traffic to both backends

- ✓ Failover/recovery scenarios validated